## Project schedule
| WW1 Database | [5 empty] | Project start: | [7 empty] | 2025-02-14
[7 empty] | Display week: | [7 empty] | 1
[7 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-02-10 to 2025-04-06
 | time axis 2025-02-10 to 2025-04-06
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Part 1 of the Prjoect deadline 7th march
| Developing WW1 Database | Amaan Mahmood | 100% | 2025-02-18 | 2025-02-27 | 10 | bar: 2025-02-20; 2025-02-27
| linking ww1 database and creating search page | Hassan Raza | 100% | 2025-02-27 | 2025-03-02 | 4
| Designing and devolping home page and work on database | Mehdi Bukhari | 100% | 2025-02-20 | 2025-03-02 | 11
| work on javascript and frontend | Fahad Khan | 100% | 2025-02-21 | 2025-02-28 | 8
| Design and develop about us page and work/connect login | Sulaiman Saeed | 100% | 2025-02-21 | 2025-03-02
| Work on Front end and team minutes | Adam Sajad | 100% | 2025-02-27 | 2025-03-05
| creating Login page to database and create database for login | Fizzah Khan | 100% | 2025-02-26 | 2025-03-02 | 5
Part 2 of the project
|  | Amaan Mahmood | 0%
|  | Hassan Raza | 0%
|  | Mehdi Bukhari | 0%
|  | Fahad Khan | 0%
|  | Sulaiman Saeed | 0%
|  | Adam Sajad | 0%
|  | Fizzah Khan | 0%
|  | Amaan Mahmood | 0%
|  | Hassan Raza | 0%
|  | Mehdi Bukhari | 0%
|  | Fahad Khan | 0%
|  | Sulaiman Saeed | 0%
|  | Adam Sajad | 0%
|  | Fizzah Khan | 0%